## Test Case Format
Sr.No | Scenario Id | Scenario objective | Test Case Id | Test case Objective | Steps | Test Data | Expected Result | Actual Result | Status | Tester Name | Remark
1 | sc_01 | To verify Login functionality | tc_001 | To verify user is able to login with correct credentials | 1 Enter username 2 Enter Password 3 click on login btn | username :-Daya pass :-Daya@123 | to view the password | password unvisible as it shows " … " and not characters or alphabets | Not Done | Anjali | Characters should be visible
2 |  |  | tc_002 | weak password should not be accepted | 1 Enter username 2 Enter Password 3 click on login btn | username :-Daya pass :-123 | a message should be shown saying " weak password " | login successful | Not Done | Mansi | a message should be shown saying " weak password "
3 |  |  | tc_003 | To verify user is able to login with wrong username ,correct password | 1 Enter wrong username 2 Enter Password 3 click on login btn | username :-daya pass :-Daya@123 | forget password option must be available | forget password option not there | Not Done | Mayuri | Add foget password option
4 |  |  | tc_004 | moblie number must include only digits upto 10 | 1 Go to register 2 Enter mobile number | 12345690123 | error must be shown (number greater than 10 digits ) | login successful | Not Done | Tanishka | More than or less than 10 digits should not be aproved
5 |  |  | tc_005 | mobile number must only include digits and not alphabets | 1 Go to register 2 Enter mobile number | 12345abcde | error must be shown (alphabets should not be included ) | login successful | Not Done | Krish | Alphabets should not be allowed in phone number
6 |  |  | tc_006 | To verify if multiple users can use same mobile number | 1 Go to register 2 Enter mobile number | 1234567890 | error must be shown ( phone number already in use ) | login successful | Not Done | Anjali | Multiple users on same mobile number should not be allowed
7 |  |  | tc_007 | To verify if the mobile number is invalid | 1 Go to register 2 Enter mobile number | 11111111111 | error must be shown ( phone number is invalid ) | login successful | Not Done | Mansi | Invalid phone number should not be accepted
8 |  |  | tc_008 | To verify login | 1 Go to register 2 Enter password 3 Enter confirm password | password :- abc123 confirm password :- abc123 | Confirm password and password must be same to register successfully | login successful | Done | Mayuri | Works Properly
9 |  |  | tc_009 | To verify password veriication | 1 Go to Login page 2 Enter password | email :- abc@gmail.com password :- abc123 | Enter email and passwod on register page then on login page | login successful | Done | Tanishka | Works Properly
10 |  |  | tc_010 | To verify if it accepts invalid email | 1 Go to register 2 Enter email | daya@ab | error must be show as the email is invalid | login successful | Not Done | Krish | Include proper email validation syntax
11 | sc_02 | To verify Dashboard functionality | tc_001 | To check dashboard GUI | 1 Login 2 Go to dashboard | Display | emial lable is there but no email address is visible | email address should be visible | Not Done | Anjali | Visual bug, fix it
12 |  |  | tc_002 | To verify if Add Room feature works | 1 Login 2 Go to Dashboard 3 Go to "Add Room" | Display | Add Room feature must work properly | Add Room feature works properly | Done | Mansi | Works Properly
13 |  |  | tc_003 | To verify if My Room feature works | 1 Login 2 Go to Dashboard 3 Go to "My Room" | Display | My Room feature must work properly | My Room feature works properly | Done | Mayuri | Works Properly
14 |  |  | tc_004 | To verify if Booking Request | 1 Login 2 Go to Dashboard 3 Go to "Booking Request" | Display | Booking Request dynamically get updated | Booking Request dynamically get updated | Done | Tanishka | Works Properly
15 |  |  | tc_005 | To verify if "Update Profile" works properly | 1 Login 2 Go to Dashboard 3 Go to My Profile then "Update Profile" | Display | Update Profile works properly | Update Profile works properly | Done | Krish | Works Properly
16 |  |  | tc_002 | To check dashboard GUI ( only for owner ) | 1 Login 2 Go to Dashboard 3 Go to Owner | Display | 2 BHK should be visible only ones | 2 BHK option visible twice | Not Done | Anjali | Visual bug, fix it
17 |  |  | tc_003 | To check dashboard GUI ( only for owner ) | 1 Login 2 Go to Dashboard 3 Go to Owner | Display | If a booking is rejected in "manage booking", it must be rejected in "manage room" | If a booking is rejected in "manage booking", it shows booked in "manage room" | Not Done | Mansi | Sync dynamically
18 |  |  | tc_004 | To verify if "Edit Profile" works peoperly | 1 Login 2 Go to Dashboard 3 Go to Profile then Edit Profile | Display | Edit Profile works properly | Edit Profile works properly | Done | Mayuri | Works Properly
19 |  |  | tc_005 | To check dashboard GUI ( only for customer ) | 1 Login 2 Go to Dashboard 3 Go to Customer | Display | If we are in the "my booking" section, status should be visible | If we are in the "my booking" section, status is not visible | Not Done | Tanishka | Sync dynamically
20 |  |  | tc_006 | To check dashboard GUI ( only for customer ) | 1 Login 2 Go to Dashboard 3 Go to Customer | Display | If we are in the "my booking" section and "my profile" section, the dashboard should show "my booking" and "my profile" respectively | If we are in the "my booking" section and "my profile" section, the dashboard shows available rooms | Not Done | Krish | GUI bug
21 |  |  | tc_007 | To check dashboard GUI ( only for owner ) | 1 Login 2 Go to Dashboard 3 Go to Owner | Display | Multiple images should be uploded | Multiple images cannot be uploded | Not Done | Anjali | Allow multiple images to upload
22 |  |  | tc_008 | To check dashboard GUI ( only for owner ) | 1 Login 2 Go to Dashboard 3 Go to Owner | Display | If the rent is too high, it is accepted but the amount shown on customer section should not be different | If the rent is too high, it is accepted but the amount shown on customer section is different | Not Done | Mansi | Backend bug ( show the actual price set by the owner on customer page )
23 |  |  | tc_009 | To check dashboard GUI ( only for owner ) | 1 Login 2 Go to Dashboard 3 Go to Owner | Display | If the owner and customer made a deal on an aggrement then the admin should not have the right to delete it. | If the owner and customer made a deal on an aggrement then the admin has option to delete it | Not Done | Mayuri | The admin should not have the right to delete the aggrement done by the owner and the customer
24 |  |  | tc_010 | To check dashboard GUI ( only for owner ) | 1 Login 2 Go to Dashboard 3 Go to Owner | Display | When the customer books a room, it should get updated on "Owner Dashboard" | When the customer books a room, it does not get updated on "Owner Dashboard" | Not Done | Tanishka | GUI bug
25 |  |  | tc_011 | To verify is "Proerty Owner Management" is correct | 1 Login 2 Go to Dashboard 3 Go to Manage Users then Property Owners | Display | Property Owner Management feature works correctly | Property Owner Management feature works correctly | Done | Krish | Works Properly
26 |  |  | tc_012 | To verify "Manage Rooms" feature is correct | 1 Login 2 Go to Dashboard 3 Go to Manage Rooms | Display | Manage Rooms feature works properly | Manage Rooms feature works properly | Done | Anjali | Works Properly
27 |  |  | tc_013 | To verify "Search Bar" feature works correctly for all | 1 Login 2 Go to Dashboard 3 Go to Search Bar | Display | Search Bar feature works correctly | Search Bar feature works correctly | Done | Mansi | Works Properly
28 |  |  | tc_014 | To verify is "Category" feature works correctly | 1 Login 2 Go to Dashboard 3 Go to Category | Display | Category feature works correctly (property gets added and deleted) | Category feature works correctly (property gets added and deleted) | Done | Mayuri | Works Properly
29 |  |  | tc_015 | To verify if "Add Location" feature works properly | 1 Login 2 Go to Dashboard 3 Go to Location | Display | Add Location feature works properly | Add Location feature works properly | Done | Tanishka | Works Properly
30 |  |  | tc_016 | To verify if "Print Report" feature works properly | 1 Login 2 Go to Dashboard 3 Go to Reports then click on Print Report | Print Report | Print Repost feature works properly | Print Repost feature works properly | Done | Krish | Works Properly
31 |  |  | tc_017 | To verify is "Logout" button works properly | 1 Login 2 Go to Dashboard 3 Click on Logout | Logout | Logs out successfully | Logs out successfully | Done | Anjali | Works Properly
32 |  |  | tc_018 | To check dashboard GUI ( only for admin ) | 1 Login 2 Go to Admin Dashboard 3 Go to Manage Users then Customers | Display | The admin should not get logged out | The admin gets logged out acutomatically | Not Done | Mansi | While going on the customer page from Manage Users, gets logged out automatically
33 |  |  | tc_019 | To check dashboard GUI ( only for admin ) | 1 Login 2 Go to Admin Dashboard 3 Go to Bookings then Manage Bookings | Display | If a property is rejected in "Manage Bookings" then it should show the same in "Manage Rooms" | If a property is rejected in "Manage Bookings" then it shows booked in "Manage Rooms" | Not Done | Mayuri | Backend bug
34 |  |  | tc_020 | To check dashboard GUI ( only for admin ) | 1 Login 2 Go to Admin Dashboard 3 Go to Bookings then Manage Bookings | Display | If the admin deletes a proprty in manage bookings section, it should get deleted in customer and owner page. | If the admin deletes a proprty in manage bookings section, it does not get deleted in customer and owner page. | Not Done | Tanishka | Backend bug
35 |  |  | tc_021 | To check dashboard GUI ( only for admin ) | 1 Login 2 Go to Admin Dashboard | Display | While counting the total users, it should not count the admin. | While counting the total users, it counts the admin as well. | Not Done | Krish | While counting the total usrs only count the total owners and the customers
36 | sc_03 | To verify update functionality | tc_001 | To verify Customer Profile | 1 Login 2 Go to Costumer Dashboard 3 Go to Customer Profile | current password :- abc123 new password :- abc123 | While updating the current password to a new password, it should not accept the old password. | While updating the current password to a new password, it accepts the old password too. | Not Done | Anjali | While updating the current password to a new password, it should not accept the old password.
37 |  |  | tc_002 | To check dashboard GUI ( only for owner ) | 1 Login 2 Go to Dashboard 3 Go to Owner | Feature date unavailable. | Change password feature should be available on Customer Profile. | Change password feature not available on Customer Profile. | Not Done | Mansi | Change password feature should be available on Customer Profile.
38 | sc_04 | To verify Security Functionality | tc_001 | To check security feature | 1 Click on URL 2 Edit URL | Edited URL - flatfinder/admin/dashboard | Should not allow access to admin page without login | Allows access to admin page without login | Not Done | Mayuri | Security Bug

## Bug Report
Sc_ID | TC_ID | User Type | Bug Id | Bug Description | Feature Name | Page Name | Priority | Allocated To | Developer Status | Tester Status | Tester Name | Remark
sc_01G12E2A2:G15A2:H17E2A2:G15A2:I17A2:I17 | tc_001 | User | bug_01 | password unvisible as it shows " ... " and not characters or alphabets | Login | login.php | P2 |  | Open | Fail | Anjali | Needs Inprovment
sc_01 | tc_002 | User | bug_02 | forget password option must be available | Login | login.php | P2 |  | Open | Fail | Mansi | Needs Inprovment
sc_01 | tc_004 | User | bug_04 | error must be shown (number greater than 10 digits ) | Login | login.php | P2 |  | Open | Fail | Tanishka | Needs Inprovment
sc_01 | tc_005 | User | bug_05 | error must be shown (alphabets should not be included ) | Registration | register.php | P2 |  | Open | Fail | Krish | Needs Inprovment
sc_01 | tc_006 | User | bug_06 | error must be shown ( phone number already in use ) | Registration | register.php | P2 |  | Open | Fail | Anjali | Needs Inprovment
sc_01 | tc_007 | User | bug_07 | error must be shown ( phone number is invalid ) | Registration | register.php | P2 |  | Open | Fail | Mansi | Needs Inprovment
sc_01 | tc_010 | User | bug_08 | error must be show as the email is invalid | Registration | register.php | P2 |  | Open | Fail | Krish | Needs Inprovment
sc_02 | tc_001 | User | bug_09 | email address should be visible | Dashboard | dashboard.php | P3 |  | Open | Fail | Anjali | Needs Inprovment
sc_02 | tc_002 | Owner | bug_10 | 2 BHK option visible twice | Dashboard | owner_dashboard.php | P3 |  | Open | Fail | Anjali | Needs Inprovment
sc_02 | tc_003 | Owner | bug_11 | If a booking is rejected in "manage booking", it shows booked in "manage room" | Dashboard | owner_dashboard.php | P3 |  | Open | Fail | Mansi | Needs Inprovment
sc_02 | tc_005 | Customer | bug_12 | If we are in the "my booking" section, status is not visible | Dashboard | customer_dashboard.php | P3 |  | Open | Fail | Tanishka | Needs Inprovment
sc_02 | tc_006 | Customer | bug_13 | If we are in the "my booking" section and "my profile" section, the dashboard shows available rooms | Dashboard | customer_dashboard.php | P3 |  | Open | Fail | Krish | Needs Inprovment
sc_02 | tc_007 | Owner | bug_14 | Multiple images cannot be uploded | Dashboard | owner_dashboard.php | P3 |  | Open | Fail | Anjali | Needs Inprovment
sc_02 | tc_008 | Owner | bug_15 | If the rent is too high, it is accepted but the amount shown on customer section is different | Dashboard | owner_dashboard.php | P3 |  | Open | Fail | Mansi | Needs Inprovment
sc_02 | tc_009 | Owner | bug_16 | If the owner and customer made a deal on an aggrement then the admin has option to delete it | Dashboard | owner_dashboard.php | P3 |  | Open | Fail | Mayuri | Needs Inprovment
sc_02 | tc_010 | Owner | bug_17 | When the customer books a room, it does not get updated on "Owner Dashboard" | Dashboard | owner_dashboard.php | P3 |  | Open | Fail | Tanishka | Needs Inprovment
sc_02 | tc_018 | Admin | bug_18 | The admin gets logged out acutomatically | Dashboard | admin_dashboard.php | P1 |  | Open | Fail | Mansi | Needs Inprovment
sc_02 | tc_019 | Admin | bug_19 | If a property is rejected in "Manage Bookings" then it shows booked in "Manage Rooms" | Dashboard | admin_dashboard.php | P3 |  | Open | Fail | Mayuri | Needs Inprovment
sc_02 | tc_020 | Admin | bug_20 | If the admin delets a proprty in manage bookings section, it does not get deleted in customer and owner page. | Dashboard | admin_dashboard.php | P3 |  | Open | Fail | Tanishka | Needs Inprovment
sc_02 | tc_021 | Admin | bug_21 | While counting the total users, it counts the admin as well. | Dashboard | admin_dashboard.php | P3 |  | Open | Fail | Krish | Needs Inprovment
sc_03 | tc_001 | Customer | bug_22 | While updating the current password to a new password, it accepts the old password too. | Profile Management | profile.php | P2 |  | Open | Fail | Anjali | Needs Inprovment
sc_03 | tc_002 | Owner | bug_23 | Change password feature not available on Customer Profile. | Profile Management | profile.php | P3 |  | Open | Fail | Mansi | Needs Inprovment
sc_04 | tc_001 | User | bug_24 | Allows access to admin page without login | Security / URL Access | admin/dashboard.php | P1 |  | Open | Fail | Mayuri | Needs Inprovment